## Schedule
WBS | Task Name | Type | Category | Start | End | Duration | % | Status | Assignee
1 | 15FL - New Office | parent | General | 01-05-2026 | 15-09-2026 | 138d | 0% | Not Started
1.1 | Propose final layout | task | General | 01-05-2026 | 20-05-2026 | 20d | 0% | Not Started
1.2 | Price Comparison | task | General | 01-06-2026 | 20-06-2026 | 20d | 0% | Not Started
1.3 | Demolish & Construction period (1.5 months) | task | General | 01-07-2026 | 14-08-2026 | 45d | 0% | Not Started
1.4 | Furniture | task | General | 15-08-2026 | 03-09-2026 | 20d | 0% | Not Started
1.5 | Move - in | milestone | General | 15-09-2026 | 15-09-2026 | 1d | 0% | Not Started
2 | 12FL - Umami Kitchen | parent | General | 01-06-2026 | 15-11-2026 | 168d | 0% | Not Started
2.1 | Propose final layout | task | General | 01-06-2026 | 20-06-2026 | 20d | 0% | Not Started
2.2 | Bidding Process | task | General | 01-07-2026 | 20-07-2026 | 20d | 0% | Not Started
2.3 | Demolish & Construction period (3 months) | task | General | 01-08-2026 | 29-10-2026 | 90d | 0% | Not Started
2.4 | Furniture | task | General | 15-10-2026 | 03-11-2026 | 20d | 0% | Not Started
2.5 | Move - in | milestone | General | 15-11-2026 | 15-11-2026 | 1d | 0% | Not Started
3 | 12FL - Umai Kitchen | parent | General | 01-06-2026 | 15-11-2026 | 168d | 0% | Not Started
3.1 | Propose final layout | task | General | 01-06-2026 | 20-06-2026 | 20d | 0% | Not Started
3.2 | Price Comparison | task | General | 01-07-2026 | 20-07-2026 | 20d | 0% | Not Started
3.3 | Demolish & Construction period (3 months) | task | General | 01-08-2026 | 29-10-2026 | 90d | 0% | Not Started
3.4 | Move - in | milestone | General | 15-11-2026 | 15-11-2026 | 1d | 0% | Not Started
4 | 12FL - Office | parent | General | 01-06-2026 | 15-11-2026 | 168d | 0% | Not Started
4.1 | Propose final layout | task | General | 01-06-2026 | 20-06-2026 | 20d | 0% | Not Started
4.2 | Price Comparison | task | General | 01-07-2026 | 20-07-2026 | 20d | 0% | Not Started
4.3 | Demolish & Construction period (2 months) | task | General | 01-08-2026 | 29-09-2026 | 60d | 0% | Not Started
4.4 | Furniture | task | General | 01-10-2026 | 20-10-2026 | 20d | 0% | Not Started
4.5 | Move - in | milestone | General | 15-11-2026 | 15-11-2026 | 1d | 0% | Not Started